## PERT Schedule
Task | Description | Predecessor | Successor | Optimistic Time | Most Likely Time | Pessimistic Time | ET | ES | EF | LS | LF | Slack
Planning Phase
A | Defining System Objectives and Scope | None | B | 3 | 4 | 5 | 4 | 0 | 4 | 0 | 4 | 0
B | Identifying Project Hardware and Software Components | A | C | 3 | 4 | 5 | 4 | 4 | 8 | 4 | 8 | 0
C | Conduct Feasibility Study | B | D | 2 | 3 | 7 | 4 | 8 | 12 | 8 | 12 | 0
D | Create Project Timeline | C | E,F | 1 | 2 | 5 | 2 | 12 | 14 | 12 | 14 | 0
Design Phase
E | Design System Prototype | D | G | 3 | 4 | 9 | 5 | 14 | 19 | 14 | 19 | 0
F | Design User Interface (UI) | D | G | 3 | 4 | 5 | 4 | 14 | 18 | 15 | 19 | 1
G | Design Integrations of API and Libraries | E,F | H,I | 2 | 3 | 5 | 3 | 19 | 22 | 19 | 22 | 0
Development Phase
H | Develop Frontend and API | G | J | 2 | 3 | 8 | 4 | 22 | 26 | 23 | 27 | 1
I | Develop Backend | G | J | 3 | 5 | 9 | 5 | 22 | 27 | 22 | 27 | 0
J | Develop Prototype | H,I | K,L | 2 | 4 | 7 | 4 | 27 | 31 | 27 | 31 | 0
Testing Phase
K | Conduct Testing and Trials | J | M | 2 | 3 | 5 | 3 | 31 | 34 | 32 | 35 | 1
L | Fix Hardware and Software Issues | J | M | 2 | 4 | 6 | 4 | 31 | 35 | 31 | 35 | 0
M | Conduct User Testing and Evaluate User Acceptance | K,L | N | 1 | 3 | 5 | 3 | 35 | 38 | 35 | 38 | 0
N | Deploy Final System | M | O | 2 | 4 | 5 | 4 | 38 | 42 | 38 | 42 | 0
Deployment Phase
O | Prepare System Documentation | N | None | 3 | 4 | 6 | 4 | 42 | 46 | 42 | 46 | 0

## PERT Diagram
[12 empty] | 14 | 5 | 19 |  |  |  | 22 | 4 | 26 |  |  |  | 31 | 3 | 34
[12 empty] | E | [5 empty] | H | [5 empty] | K
[12 empty] | 14 | 0 | 19 |  |  |  | 23 | 1 | 27 |  |  |  | 32 | 1 | 35
0 | 4 | 4 | 4 | 4 | 8 | 8 | 4 | 12 | 12 | 2 | 14 |  |  |  | 19 | 3 | 22 |  |  |  | 27 | 4 | 31 |  |  |  | 35 | 3 | 38 | 38 | 4 | 42 | 42 | 4 | 46
A |  |  | B |  |  | C |  |  | D | [5 empty] | G | [5 empty] | J | [5 empty] | M |  |  | N |  |  | O
0 | 0 | 4 | 4 | 0 | 8 | 8 | 0 | 12 | 12 | 0 | 14 |  |  |  | 19 | 0 | 22 |  |  |  | 27 | 0 | 31 |  |  |  | 35 | 0 | 38 | 38 | 0 | 42 | 42 | 0 | 46
[12 empty] | 14 | 4 | 18 |  |  |  | 22 | 5 | 27 |  |  |  | 31 | 4 | 35
[12 empty] | F | [5 empty] | I | [5 empty] | L
[12 empty] | 15 | 1 | 19 |  |  |  | 22 | 0 | 27 |  |  |  | 31 | 0 | 35
Critical Path (46 weeks)
A -> B -> C -> D -> E -> G -> I -> J -> L -> M -> N -> O

## Gantt Chart
Week
Task | Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46
Planning Phase
A | Defining System Objectives and Scope | bar: Week 1 to Week 4
B | Identifying Project Hardware and Software Components | bar: Week 5 to Week 8
C | Conduct Feasibility Study | bar: Week 9 to Week 12
D | Create Project Timeline | bar: Week 13 to Week 14
Design Phase
E | Design System Prototype | bar: Week 15 to Week 19
F | Design User Interface (UI) | bar: Week 15 to Week 18
G | Design Integrations of API and Libraries | bar: Week 20 to Week 22
Development Phase
H | Develop Frontend and API | bar: Week 23 to Week 26
I | Develop Backend | bar: Week 23 to Week 27
J | Develop Prototype | bar: Week 28 to Week 31
Testing Phase
K | Conduct Testing and Trials | bar: Week 32 to Week 34
L | Fix Hardware and Software Issues | bar: Week 32 to Week 35
M | Conduct User Testing and Evaluate User Acceptance | bar: Week 36 to Week 38
N | Deploy Final System | bar: Week 39 to Week 42
Deployment Phase
O | Prepare System Documentation | bar: Week 43 to Week 46